## Read Me
Read Me
WholeCart B2B Marketplace ¦ QA interview submission workbook. Update execution status and evidence before submission.
Item | Details
Purpose | Submission workbook covering questions/assumptions, test plan, scenario matrix, detailed test cases, defect log, automation plan, load plan, results report and 5-minute recording outline.
Evidence integrity | No live execution, browser capture, API request/response or load test was performed while creating this workbook. Defect log entries are candidate verification targets, NOT confirmed defects.
Environment | Target URL: http://13.200.185.1/c/omkar-6c7c41/ . Record actual build/version, browser, OS, timezone and timestamp during execution.
Credentials | Use supplied demo accounts, but never store passwords, bearer tokens or API keys in this workbook or source control. Use environment variables/CI secrets.
Evidence | For each confirmed defect, save screenshot/short recording and/or sanitized request/response. Enter exact evidence path in Defect Log. Do not submit candidates as found defects.
Performance safety | Load plan never exceeds 50 requests/second. Run only with explicit permission against the designated demo environment.
Automation status | Workbook contains a proposed automation design and commands, not a verified runnable test repository. Implement and run before claiming automation completion.
Release status | Not assessed. No release recommendation can be made until execution results and evidence are recorded.

## Questions Assumptions
Questions Assumptions
Questions to resolve with the product owner; provisional assumptions enable testing but are not substitutes for approved rules.
ID | Area | Question | Working assumption | Test implication | Status | Risk
QA-001 | Checkout | What is the exact per-seller minimum order value in BR-04? | Use only the value confirmed in the complete source; don't invent a threshold. | Test below/equal/above confirmed value. | Open | High
QA-002 | Multi-seller checkout | Is checkout atomic across seller sub-orders, or can some succeed while others fail? | No silent partial success; outcome must be explicit. | Induce one seller failure and inspect parent/sub-orders, stock and messaging. | Open | Critical
QA-003 | Delivery capacity | Does the limit of five count parent checkouts, seller sub-orders or delivery stops? | Capacity unit requires confirmation. | Multi-seller checkout near capacity. | Open | Critical
QA-004 | Cut-off | Does 10:00 cutoff apply only to same-day booking? What happens exactly at 10:00? | Boundary must be deterministic; use marketplace timezone. | Test just before/at/after cutoff for today and future dates. | Open | High
QA-005 | Timezone | Which timezone governs slots, cutoff and cancellation? | Assume marketplace local time until confirmed. | Compare UI and API timestamps. | Open | High
QA-006 | Inventory | When is stock reserved/deducted? | No committed orders may exceed available stock. | Concurrent checkout and cancellation; inspect stock before/after. | Open | Critical
QA-007 | Case/piece conversion | Can buyers order fractional cases? How do case_size, case_price and piece stock interact? | Stock tracked in pieces; product-specific case size. | Test conversion, invalid fractions and stock decrement. | Open | High
QA-008 | Tax | Are discounts applied before tax? How are mixed rates aggregated? | Aggregate net by tax rate and round half-up once per rate. | Compare independent Decimal calculation to API/UI/invoice. | Open | High
QA-009 | Delivery fee | Is ₹3,000 threshold per seller net value before tax and excluding fee? | Assume yes per documented rule; confirm. | Test ₹2,999.99 / ₹3,000.00 / ₹3,000.01 per seller. | Open | High
QA-010 | Cancellation | Is the five-minute boundary inclusive and what timestamp starts it? | Use server-side creation timestamp; clarify boundary. | Test 4:59 / 5:00 / 5:01. | Open | High
QA-011 | Order state | Which roles can cancel placed/accepted orders? Any other transition rules? | Use documented transitions, enforce actor + state. | Build allowed/disallowed transition matrix. | Open | Critical
QA-012 | Redelivery | Does failed delivery release old slot capacity? | New slot must be valid and capacity-controlled. | Inspect old/new slot counts after redelivery. | Open | High
QA-013 | Reorder | What if historical products are unavailable or prices/taxes changed? | Validate current availability/pricing at reorder/checkout; don't change historical order. | Reorder mixed available/unavailable lines. | Open | High
QA-014 | Refunds | Can overlapping partial refunds target the same line? | Cumulative approved refund cannot exceed eligible quantity/value. | Test duplicate/overlapping requests. | Open | Critical
QA-015 | Statement | Which date determines statement month and how are later-approved refunds treated? | Delivered order month as documented; refund policy needs confirmation. | Test month boundary and later refund approval. | Open | High
QA-016 | Partner exactly-once | What mechanism and dedupe key prevent duplicate downstream orders? | Retries must not create duplicate logical orders. | Repeat partner fetch/event delivery as supported. | Open | Critical
QA-017 | Rate limit | Is 50 RPS global, per API key, user or endpoint? | Never exceed 50 RPS overall in this exercise. | Ramp only up to 50 RPS and document observed behaviour. | Open | High
QA-018 | API contract | What are exact login response fields, error schema and status codes? | Swagger/OpenAPI is source of truth. | Validate schema before assertions. | Open | High
QA-019 | CSV import | Are valid rows committed when other rows fail? | Every invalid row must be reported; atomicity unknown. | Mixed-validity import and post-import reconciliation. | Open | High
QA-020 | Operator settings | How do setting changes affect in-flight checkouts? | New setting should apply to subsequent server validation; existing order consistency preserved. | Change setting while checkout is open. | Open | High
QA-021 | Metrics | Is /api/metrics authenticated and what fields should it expose? | Follow environment access policy; no secrets/PII. | Check permissions and response contents. | Open | Medium
QA-022 | Environment | What build, seed data, reset process and test window are available? | Record actual metadata; don't assume stable seed data. | Capture in every test run/defect. | Open | High

## Test Plan
Test Plan
One-page risk-based plan. Confirm exact thresholds and state transitions against approved requirements before execution.
Section | Plan
Objective | Validate buyer/seller/operator workflows, business rules, role permissions, API contract, data integrity, integrations and specified performance targets.
Scope | Authentication; catalogue/search; cart/checkout; multi-seller sub-orders; stock/case conversion; slots/cutoff; order lifecycle/cancel/redelivery/reorder; refunds/exchanges; invoices/statements; seller products/CSV; operator settings/export; partner API; /api/metrics; RBAC; bounded performance.
Approach | Review spec/API contract; role smoke tests; P0/P1 E2E and API; negative/boundary/RBAC; concurrency; approved load <=50 RPS; reconcile order, inventory and financial records; attach evidence.
Entry criteria | App reachable; approved test window; valid accounts; API contract available; known test data/reset process; environment/version captured; permission for concurrency/load.
Exit criteria | All P0 tests pass; P1 executed or blocked with rationale; no unresolved Critical defect; High risks accepted/mitigated; financial/order/inventory invariants hold; performance measured; evidence and report complete.
Risks | Shared demo data; unknown stock/slot state; ambiguous rules; HTTP URL; concurrent test interference; incomplete schemas; limited backend observability; shared-environment load variability.
Severity | Critical: money/order/inventory integrity or broad unauthorized access. High: major workflow blocked/cross-tenant exposure. Medium: limited issue with workaround. Low: cosmetic/usability.
Deliverables | Question/assumption log, plan, scenarios/matrix, test cases, evidence-backed defect log, automation repository/instructions, load script/results, results report, 5-minute recording.
Environment capture | Base URL; build/commit; timestamp/timezone; browser/version; OS; account alias only; test data IDs; API base path; tool versions.

## Scenario Matrix
Scenario Matrix
Scenario-to-test coverage map. Mark status after execution; Not Run is the initial state.
Scenario ID | Scenario | Roles | Layer | Priority | Risk area | Test IDs | Status
SC-001 | Login valid/invalid for each role | Buyer/Seller/Operator | UI+API | P0 | Auth | TC-001; TC-002 | Not Run
SC-002 | Buyer cannot access another buyer's orders/invoices/statements | Buyer | API+UI | P0 | RBAC | TC-003; TC-004 | Not Run
SC-003 | Seller cannot access another seller's orders/products | Seller | API+UI | P0 | RBAC | TC-005; TC-006 | Not Run
SC-004 | Operator-only settings/export | Operator | API+UI | P0 | RBAC | TC-007 | Not Run
SC-005 | Out-of-stock product excluded from catalogue/search | Buyer | UI+API | P1 | Catalogue | TC-008 | Not Run
SC-006 | Quantity 1/99 accepted; 0/100/negative rejected | Buyer | UI+API | P1 | Cart | TC-009 | Not Run
SC-007 | Multi-seller checkout creates correct sub-orders | Buyer | UI+API | P0 | Checkout | TC-010 | Not Run
SC-008 | Per-seller minimum and delivery-fee boundary | Buyer | API+UI | P0 | Pricing | TC-011; TC-012 | Not Run
SC-009 | Mixed tax, half-up rounding and invoice reconciliation | Buyer | API+UI | P0 | Finance | TC-013 | Not Run
SC-010 | Duplicate checkout/retry produces one logical order | Buyer | API | P0 | Idempotency | TC-014 | Not Run
SC-011 | Concurrent buyers cannot oversell | Buyer | API/Load | P0 | Concurrency | TC-015 | Not Run
SC-012 | Slot date windows, capacity and cutoff | Buyer/Operator | UI+API | P0 | Delivery | TC-016; TC-017 | Not Run
SC-013 | Allowed/disallowed order transitions | Buyer/Seller | API+UI | P0 | Lifecycle | TC-018 | Not Run
SC-014 | Five-minute cancellation boundary | Buyer | API+UI | P1 | Cancellation | TC-019 | Not Run
SC-015 | Failed delivery and redelivery slot | Buyer/Seller | API+UI | P1 | Recovery | TC-020 | Not Run
SC-016 | Reorder all lines and unavailable item | Buyer | API+UI | P1 | Reorder | TC-021 | Not Run
SC-017 | Refund eligibility/quantities/duplicate requests | Buyer/Seller | API+UI | P0 | Refund | TC-022; TC-023 | Not Run
SC-018 | Invoice required fields and totals | Buyer | API+UI | P0 | Invoice | TC-024 | Not Run
SC-019 | Statement month boundary/cancelled/refunded orders | Buyer | API | P1 | Statement | TC-025 | Not Run
SC-020 | CSV import schema, encoding and row errors | Seller | API+UI | P1 | Import | TC-026 | Not Run
SC-021 | Partner key, offer update, retry and ownership | Partner/Seller | API | P0 | Integration | TC-027 | Not Run
SC-022 | Logistics export status filters and columns | Operator | API+UI | P1 | Export | TC-028 | Not Run
SC-023 | Settings take effect; in-flight checkout revalidation | Operator/Buyer | API+UI | P1 | Configuration | TC-029 | Not Run
SC-024 | Search p95 <=2s; checkout 95% <=3s at 30 concurrent buyers | Buyer | Load | P1 | Performance | TC-030 | Not Run
SC-025 | Rate-limit policy and /api/metrics | API clients | Load/API | P1 | Performance/Security | TC-031 | Not Run

## Test Cases
Test Cases
Detailed specification. Actual result, evidence path and defect ID should be populated only after execution.
TC ID | Area | Test case | Priority | Type | Test data | Preconditions | Steps | Expected result | Status | Actual result | Evidence path | Defect ID
TC-001 | Authentication | Valid login for each role | P0 | Positive | buyer1/seller1/operator; password via secret store | App reachable; accounts enabled | Login; submit valid credentials; inspect role landing page. | Successful login; correct role/identity; no credential leakage. | Not Run
TC-002 | Authentication | Invalid login and missing/invalid token | P0 | Negative | Invalid password; no token; malformed token | API contract available | POST invalid login; call /api/me without and with malformed token. | Denied per contract; no protected data or side effects. | Not Run
TC-003 | RBAC | Buyer1 reads buyer2 order/invoice | P0 | Security | buyer1 token; buyer2 resource IDs | Separate records exist | Request buyer2 order/invoice as buyer1. | Denied or safe not-found per contract; no private data leaked. | Not Run
TC-004 | RBAC | Buyer order list scoped to authenticated buyer | P0 | Security | buyer1/buyer2 with distinct orders | Orders exist | Query order list as each buyer; compare IDs. | Only own orders returned. | Not Run
TC-005 | RBAC | Seller1 reads/mutates seller2 records | P0 | Security | seller1 token; seller2 order/product IDs | Seller records exist | Attempt GET and mutation with seller1 identity. | Denied; no cross-seller data exposure or mutation. | Not Run
TC-006 | Products | Seller product update validation | P1 | API | Valid values; negative price/stock; invalid tax rate | Seller owns product | PUT valid and invalid payloads; GET product after each. | Valid update persists; invalid values rejected without partial mutation. | Not Run
TC-007 | Operator RBAC | Buyer/seller cannot access settings/export | P0 | Security | Buyer/seller/operator tokens | Admin endpoints available | Try GET/PUT settings and logistics export as each role. | Non-operator denied; operator access matches contract. | Not Run
TC-008 | Catalogue | Zero-stock product hidden from search/catalogue | P1 | Functional | SKU stock=0; in-stock control SKU | Known product stock | Search and query list; compare with stock. | Out-of-stock product excluded from catalogue/search as specified. | Not Run
TC-009 | Cart | Quantity boundaries 1, 99, 0, 100, negative | P1 | Boundary | Quantities -1, 0, 1, 99, 100 | Product available | Add via UI/API and inspect cart/response. | 1 and 99 accepted subject to stock; invalid quantities rejected. | Not Run
TC-010 | Checkout | Multi-seller cart creates mapped sub-orders | P0 | E2E | Products from seller1 and seller2; known quantities | Stock/slot available; minimums met | Add products; checkout; inspect parent and sub-orders. | One correct sub-order per seller; items, quantities, IDs and totals reconcile. | Not Run
TC-011 | Pricing | Per-seller minimum order threshold | P0 | Boundary | Seller A below; seller B above confirmed threshold | Exact threshold confirmed | Build multi-seller cart and submit. | Each seller validated independently; no invalid order created. | Not Run
TC-012 | Pricing | Delivery fee threshold | P0 | Boundary | Net totals ₹2,999.99 / ₹3,000 / ₹3,000.01 per seller | Tax/fee enabled | Checkout each boundary; compare UI/API/invoice. | ₹100 + 18% fee tax only below ₹3,000, per seller sub-order. | Not Run
TC-013 | Finance | Mixed tax and half-up rounding | P0 | Calculation | ₹1,000 at 5%; ₹2,000 at 18% | Tax rules active | Calculate with Decimal; compare checkout and invoice. | Tax ₹50 + ₹360; net ₹3,000; no fee at exact threshold; total ₹3,410. | Not Run
TC-014 | Checkout | Duplicate submission/retry after timeout | P0 | Reliability | Same logical checkout payload | Safe test data | Submit checkout, retry after ambiguous response, query orders/stock. | One logical order/sub-order set; no duplicate stock deduction. | Not Run
TC-015 | Inventory | Two concurrent orders exceed remaining stock | P0 | Concurrency | Stock 5; buyer1 qty4; buyer2 qty4 | Dedicated product/reset | Submit concurrently; inspect outcomes and final stock. | Committed quantity <=5; no oversell; stock and orders reconcile. | Not Run
TC-016 | Delivery | Date horizon and four slot windows | P0 | Boundary | Today, today+7, today+8; all configured slots | Timezone known | Request allowed and invalid dates/slots. | Only documented dates/slots accepted. | Not Run
TC-017 | Delivery | Slot capacity and cutoff race | P0 | Concurrency | 4 of 5 bookings; two competing bookings; cutoff boundaries | Capacity unit/cutoff clarified | Submit concurrent bookings and test before/at/after cutoff. | Capacity never exceeded; cutoff follows approved rule. | Not Run
TC-018 | Lifecycle | Valid and invalid state transitions | P0 | State | Placed, Accepted, Shipped, Delivered, Cancelled, Failed | Known states available | Attempt valid and invalid actions; query persisted state. | Only allowed transitions by permitted actor succeed. | Not Run
TC-019 | Cancellation | Five-minute cancellation boundary | P1 | Boundary | 4:59 / 5:00 / 5:01 from server creation time | Reliable timing setup | Cancel at each boundary and inspect persisted status. | Result follows clarified inclusive boundary; backend enforces timing. | Not Run
TC-020 | Redelivery | Failed delivery then new valid slot | P1 | Recovery | Failed order; valid/full slot controls | Order setup available | Mark failed; request redelivery using valid and invalid/full slots. | Only eligible slot accepted; state and capacity consistent. | Not Run
TC-021 | Reorder | Every old line added each reorder action | P1 | Functional | Delivered multi-line order; repeat action | Historical order exists | Reorder twice; inspect cart; test unavailable item. | Every original line added each time; current availability rule applied; no order before checkout. | Not Run
TC-022 | Refund | Refund before delivery rejected | P0 | Negative | Placed, Shipped and Delivered orders | Orders in each state | Request refund/exchange for each state. | Only delivered order eligible. | Not Run
TC-023 | Refund | Partial/full refund and overlap constraints | P0 | Integrity | Delivered lines/quantities; duplicate partial requests | Seller decision available | Request full/partial, zero/negative/excess and overlapping quantities; approve/reject. | Eligible scope enforced; cumulative approved amount/quantity cannot exceed permitted balance. | Not Run
TC-024 | Invoice | Invoice fields and totals after delivery | P0 | Finance | Delivered mixed-tax order | Invoice endpoint available | Deliver order; fetch invoice; verify details/lines/tax/fee/total. | Required seller/buyer/GSTIN/address/lines/tax/fee fields; totals reconcile. | Not Run
TC-025 | Statement | Monthly statement reconciliation | P1 | Finance | Delivered, cancelled and refunded records near month boundary | Statement month rule clarified | Fetch statement and independently reconcile records. | Delivered orders included for month; cancelled excluded; approved refund policy applied. | Not Run
TC-026 | CSV | Import valid/mixed-invalid CSV | P1 | Integration | UTF-8 valid rows, invalid tax/stock, duplicate SKU | Dedicated seller/test SKUs | Upload; inspect row errors and resulting products. | Invalid rows report line/reason; valid-row handling follows policy; no silent loss. | Not Run
TC-027 | Partner API | API key, ownership, offer update and retry | P0 | Security/Integration | Valid/invalid/missing X-Api-Key; own/other offer IDs | Partner credentials available securely | Call partner endpoints; PUT offer; repeat; verify catalogue/stock. | Only authorized seller can update own offer; invalid key denied; no duplicate side effects. | Not Run
TC-028 | Export | Logistics CSV contents and format | P1 | Integration | Orders in all documented statuses | Operator access | Generate export; parse headers and rows; compare source orders. | Only specified statuses; ordered columns, UTF-8 and correct row mapping. | Not Run
TC-029 | Settings | Setting change affects in-flight checkout | P1 | Integration | Known setting; buyer checkout open | Operator/buyer sessions | Open checkout; change setting; submit; inspect result. | Immediate server-side validation per spec; no invalid booking or inconsistent order. | Not Run
TC-030 | Performance | Search and checkout latency | P1 | Performance | Representative search and independent carts | Approved window/metrics | Search workload; 30 concurrent checkouts; collect percentiles/errors/integrity. | Search p95 <=2s; 95% checkout requests <=3s at 30 concurrent buyers. | Not Run
TC-031 | Performance/Security | Rate limit and metrics endpoint | P1 | Performance/Security | Controlled API traffic; <=50 RPS overall | Approved load; metrics policy known | Ramp to max 50 RPS; inspect status/latency/metrics and sensitive data. | Never exceed 50 RPS; document rate limit/429 policy; no secrets/PII exposed. | Not Run

## Defect Log
Defect Log
Evidence-led defect register. Every row is an unverified candidate until reproduced. Do not submit these as confirmed defects without actual results and evidence.
Candidate ID | Title | Classification | Severity if confirmed | Impact | Steps to reproduce | Test data | Expected result | Actual result | Environment | Evidence status | Evidence required/path | Status | Notes
CAND-001 | Inventory oversell under concurrency | Candidate — unverified | Critical if reproduced | Potential stock/fulfilment/financial integrity breach | Set stock=5. Login buyer1 and buyer2 separately. Submit concurrent checkout qty=4 each. Query orders and stock. | Stock=5; buyer1 qty=4; buyer2 qty=4. | At most 5 pieces committed; second full-quantity order must not succeed; stock/orders reconcile. | Not executed — actual result unknown. | Record URL, build, browser, timestamp, role aliases. | Pending reproduction | Attach both request/responses, order records and stock before/after. No evidence attached yet. | Open — candidate only | BR-01 makes this a high-value verification target.
CAND-002 | Duplicate checkout after retry | Candidate — unverified | Critical if reproduced | Duplicate order, stock deduction or financial record | Submit valid checkout; simulate lost response after commit if possible; retry same logical transaction; query orders/stock. | Known cart, valid slot, same checkout intent. | Exactly one logical order/sub-order set; no duplicate stock deduction. | Not executed — actual result unknown. | Record build/API endpoint/time. | Pending reproduction | Attach sanitized requests/responses, order list and stock before/after. | Open — candidate only | BR-10 explicitly requires one order for duplicate submission.
CAND-003 | Cross-buyer or cross-seller access | Candidate — unverified | Critical/High if reproduced | Unauthorized data disclosure or mutation | As buyer1 request buyer2 order/invoice; as seller1 request/mutate seller2 order/product. | Distinct records and role tokens. | Denied or safe not-found per contract; no sensitive data or mutation. | Not executed — actual result unknown. | Record endpoint, role alias, build/time; redact tokens. | Pending reproduction | Attach sanitized request/response proving exposure or denial; no raw tokens. | Open — candidate only | Security verification target; not a confirmed defect.
CAND-004 | Delivery-slot overbooking | Candidate — unverified | Critical if reproduced | Delivery capacity exceeded | Create/identify slot with 4 of 5 bookings; send two competing bookings for final place; count resulting bookings. | Slot capacity=5; capacity unit clarified. | Capacity never exceeds five according to agreed capacity unit. | Not executed — actual result unknown. | Record date/timezone/slot/build. | Pending reproduction | Attach booking responses, counts and concurrency logs. | Open — candidate only | Clarify whether capacity counts checkout, sub-order or stop.
CAND-005 | Tax or delivery-fee mismatch | Candidate — unverified | High if reproduced | Incorrect customer charge or invoice/statement | Use per-seller net totals 2999.99, 3000.00, 3000.01 with mixed rates; compare independent Decimal result to checkout/API/invoice. | Known prices/rates; threshold rules confirmed. | Fee 100 + 18% fee tax only below 3000; tax aggregation/rounding and invoice totals match spec. | Not executed — actual result unknown. | Record test data, endpoint, build/time. | Pending reproduction | Attach calculation sheet, checkout/invoice screenshots and sanitized response. | Open — candidate only | Verify exact source contract before reporting.
CAND-006 | Invalid order transition accepted | Candidate — unverified | High if reproduced | Impossible states or bypassed business rules | Attempt invalid transition such as Shipped→Cancelled or Placed→Delivered; query persisted state. | Order in known starting state; permitted test identity. | Only documented transitions by permitted actors succeed; invalid attempts do not change state. | Not executed — actual result unknown. | Record order test ID, endpoint, status, build/time. | Pending reproduction | Attach request/response and before/after state. | Open — candidate only | Validate complete state machine first.
CAND-007 | CSV import silently drops or misreports rows | Candidate — unverified | High if reproduced | Catalog corruption or missing products | Upload UTF-8 CSV with valid rows and invalid tax/stock plus duplicate SKU; compare row report and product list. | Dedicated seller/test SKUs; atomicity policy clarified. | Every invalid row has line/reason; valid rows handled per policy; no silent loss/cross-seller overwrite. | Not executed — actual result unknown. | Record file name/hash, seller alias, build/time. | Pending reproduction | Attach sanitized CSV, import result and post-import records. | Open — candidate only | Mixed-validity atomicity remains an assumption.
CAND-008 | Invoice/monthly statement reconciliation | Candidate — unverified | High if reproduced | Financial reporting mismatch | Deliver mixed-tax order; where permitted add approved partial refund; compare order, invoice and statement to independent calculation. | Controlled order/refund; statement month known. | Invoice matches order; statement follows delivered/cancelled/refund rules. | Not executed — actual result unknown. | Record month/timezone, test order IDs, build. | Pending reproduction | Attach invoice/statement screenshots, sanitized API response and calculation. | Open — candidate only | Later-month refund treatment needs clarification.

## Automation
Automation
Automation plan and one-command run instructions. Implement repository and verify commands before claiming automation is delivered.
Topic | Instruction
Stack | Python 3.11+, pytest, Playwright Python, requests; optional JUnit XML/Allure; JMeter or Locust for controlled load.
Structure | tests/ui, tests/api, tests/integration, pages, clients, fixtures, data, utils, conftest.py, pytest.ini, requirements.txt, README.md.
Secrets | BASE_URL, role usernames/passwords and partner API key from environment variables or CI secret store. Never commit secrets.
Install | python -m venv .venv; activate; pip install -r requirements.txt; playwright install chromium
Run regression | pytest -m regression --junitxml=artifacts/junit.xml
Run API smoke | pytest tests/api -m smoke -q
Run UI smoke | pytest tests/ui -m smoke --browser chromium
Run one test | pytest tests/api/test_checkout.py::test_duplicate_checkout_is_idempotent -vv
Markers | smoke, regression, api, ui, integration, security, concurrency, performance. Keep performance in a separate approved job.
Fixtures | API client; buyer/seller/operator auth; isolated browser context; test-data factory; cleanup; Decimal calculation helper.
Assertions | Validate status, schema, business invariants, ownership and persistence—not just HTTP 200. Capture sanitized request/response and Playwright trace on failure.
Isolation | Use unique test SKUs/orders; dedicated stock-race products; controlled slots. Do not let unrelated parallel tests share the last stock unit or slot.
Regression scope | TC-001–TC-029 P0/P1. Execute TC-030/031 separately under controlled performance window.
Evidence | Save traces/screenshots and sanitized API logs under artifacts/<run-id>/ and link exact paths in test/defect sheets.
Status | Not implemented or executed by workbook creation. This is a target design/run contract, not proof of a runnable repository.

## Load Test
Load Test
Bounded load-test plan. Results remain blank until a permitted run; do not exceed 50 requests/second.
Test ID | Objective | Workload | Plan | Rate cap | Measurements | Acceptance criteria | Status | Actual results | Evidence path | Conclusion
LT-001 | Search latency | Representative catalogue search queries | Warm up, then ramp 5→10→20→30→40→50 RPS overall; 2–3 min/stage | Never >50 RPS | p50/p95/p99, throughput, errors, correctness, /api/metrics | Search p95 <=2 seconds | Not Run
LT-002 | Checkout latency | 30 concurrent buyers, independent valid carts/slots | 30 VUs; control arrival so aggregate rate <=50 RPS; short steady period | Never >50 RPS | Percentiles, throughput, errors, duplicate orders, stock/slot reconciliation | 95% checkout submissions <=3 seconds; integrity preserved | Not Run
LT-003 | Rate-limit behaviour | Controlled endpoint requests | Ramp gradually to but not above 50 RPS; do not exceed without permission | Never >50 RPS | Status codes, latency, throttling headers if any, metrics | Document observed policy and 429 behaviour; rejected calls have no side effects | Not Run
LT-004 | Short endurance | Representative read-only search/catalogue traffic | Up to 30 RPS for 15 minutes if approved | Never >50 RPS | Latency trend, errors, metrics; system resource metrics if available | No progressive degradation; correctness maintained | Not Run
Execution note | Use a global throughput cap. Exclude warm-up from percentile calculations. Record request mix, duration, concurrency, environment, test data and metrics response. Run only with permission; never use production.

## Results Report
Results Report
Execution summary template. Update only with evidence from the actual run.
Metric | Current value / decision
Environment | Not recorded; populate after execution.
Build/version | Not recorded; capture deployed build/commit.
Test window | Not executed.
Planned test cases | 31 detailed cases in Test Cases sheet.
Executed / Passed / Failed / Blocked | 0 / 0 / 0 / 0 — workbook preparation only.
Coverage | 25 scenario groups defined; actual coverage requires execution and status updates.
Defect counts by severity | Not assessed. Candidate targets are not confirmed defects and must not be counted as found defects.
Open risks | Minimum order threshold; checkout atomicity; slot capacity unit; stock reservation timing; cancellation boundary; refund accounting; statement month policy; partner retry/dedupe; rate-limit scope.
Performance | Not run. Search p95 <=2s; 95% checkout <=3s with 30 concurrent buyers; traffic capped at 50 RPS.
Security | Not run. Verify cross-tenant access, role permissions, partner key and metrics exposure.
Release recommendation | NOT ASSESSED. No execution evidence available; do not recommend release until P0 tests, integrity checks, defect triage and performance evidence are complete.
Release gate | No open Critical defects; P0 pass; no oversell/duplicate order/financial-integrity issue; authorization tests pass; performance measured; evidence linked; High risks accepted by owner.

## Recording Outline
Recording Outline
Five-minute walkthrough outline. Replace candidates with reproduced defects and real evidence before recording.
Time | Segment | Content/evidence
0:00–0:20 | Intro | State app/build/browser and explain you will demonstrate three highest-impact reproduced defects.
0:20–1:35 | Defect 1: inventory concurrency | Show stock before, concurrent buyer requests, responses, resulting orders and final stock. Explain invariant and impact.
1:35–2:45 | Defect 2: duplicate checkout retry | Show first request, timeout/retry, order list and stock side effects; explain idempotency.
2:45–3:55 | Defect 3: RBAC or financial mismatch | Show only a confirmed issue; use sanitized role/record evidence or independently calculated invoice mismatch.
3:55–4:35 | AI tool error and verification | If AI was used, show a real incorrect suggestion and the requirement/evidence that disproved it. Never fabricate an AI error.
4:35–5:00 | Close | Summarise severity, business impact, reproducibility, evidence and next step.
Evidence checklist | Steps, test data, expected vs actual, severity, environment, screenshot/recording or sanitized request/response, redacted IDs/secrets.
Safety | Never expose passwords, raw tokens, API keys or real customer data. Do not present candidate issues as confirmed defects.